## Description
COMP 6700/6706 -- Software Process
Assignment: | CA04
Objective: | to gain experience with estimating size and effort.
Assignment: | The worksheets in this assignment provide you with a hypothetical historical development database as well as with a forecast of standard components for a hypothetical project. Please use this information to determine the size and effort of the project.
Notes: | - This homework assignment is be accomplished individually
Deliverables: | - This spreadsheet with "Assignment" completed.
- (Optional) Explanatory calculations on worksheets "Calc-1", "Calc-2", etc.
- When complete, upload the spreadsheet to Blackboard.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect. Use "comp6700" if a password is requested.

## Process
Process Script
Entry |  | - this spreadsheet
Tasks |  | see lecture notes
Exit |  | - complete "Assignment" worksheet
- (optional) intermediate calculations
Quality checks
General
Are all regions highlighted in yellow complete? (Either with a value, or NA if the cell is not applicable. No units of measure.)
Are supporting calculations understandable?
Size matrix
Are buckets sized by a log-normal distribution?
Component sizing
Has each new component been given a type and relative size?
Are new components sized according to the size matrix?
Size and effort calculations
Is effort based on the size of new and modified code?
Is productivity calcuated in LOC/hr?
Are correlation values based on correct data sets?
Is the range calculation valid? It is correct?
Does the Lower Prediction Interval (LPI) represent a valid value?
Activity calculations
Are the lifecycle activities distributed according to historical performance?
Useful Excel Functions
tdist
|  | parms: | t, degrees of freedom, number of tails (1 or 2)
|  | returns: | area under tails
|  | example: | "=TDIST(1.325,20,2)" yields | 0.20011
|  | note: | tdist returns the area under the tails
| tinv | parms: | probability, degrees of freedom
|  | returns: | the value of t such that the area under the T-curve from [-t,t] is the probability
|  | example: | "=TINV(0.200111,20)" yields | 1.325
|  | note: | the first parm to tinv is the total area under the tails
| correl | parms: | x's, y's
|  | returns: | correlation coefficient
|  | example: | given the data at right, | X | Y
|  |  | "=CORREL(F83:F88,G83:G88)" | 1 | 2
|  |  | yields | 2 | 4
|  |  | 0.98372 | 4 | 8
|  |  |  | 5 | 10
|  |  |  | 6 | 12
|  |  |  | 7 | 17
| average | parms: | values
|  | returns: | average of the values
|  | example: | the average of the x's above is "=AVERAGE(F42:F47)", or |  |  | 4.1667
| stdev | parms: | values
|  | returns: | standard deviation of the values
|  | example: | the std of the x's above is "=STDEV(F42:F47)", or |  |  | 2.3166
| sum | parms: | values
|  | returns: | sum of the values
|  | example: | the sum of the x's above is "=SUM(F42:F47)", which yields |  |  | 25
| ln | parms: | value
|  | returns: | natural logarithm of the value
|  | example: | the natural logarithm of the value above is "=ln(I59)", which yields |  |  | 3.2189
| exp | parms: | power
|  | returns: | 2.718**power
|  | example: | the antilog of the natural log abve "=exp(I59)", which is |  |  | 25
| ceiling | parms: | value, places
|  | returns: | a value that is rounded up to the nearest significant digit
|  | example: | the integer ceiling of 4.1667 is "=ceiling(4.1667,1)", which is: |  |  | 5

## Data
Project History: The following is a record of historical components.
| Identifier | Total Loc | Methods | Type
| Component1 | 167 | 10 | Data
| Component2 | 194 | 13 | Calculation
| Component3 | 94 | 6 | Logic
| Component4 | 130 | 9 | Data
| Component5 | 108 | 8 | I/O
| Component6 | 194 | 12 | I/O
| Component7 | 70 | 5 | I/O
| Component8 | 174 | 12 | Logic
| Component9 | 14 | 1 | Calculation
| Component10 | 164 | 11 | Data
| Component11 | 77 | 5 | Logic
| Component12 | 62 | 4 | Calculation
| Component13 | 47 | 3 | Data
| Component14 | 33 | 3 | Data
| Component15 | 54 | 3 | Calculation
| Component16 | 90 | 7 | Data
| Component17 | 76 | 4 | I/O
| Component18 | 57 | 4 | I/O
| Component19 | 110 | 7 | Data
| Component20 | 95 | 5 | Logic
| Component21 | 104 | 7 | Logic
| Component22 | 133 | 10 | Logic
| Component23 | 144 | 10 | Calculation
| Component24 | 197 | 13 | Logic
| Component25 | 144 | 11 | Logic
| Component26 | 224 | 15 | I/O
| Component27 | 38 | 2 | Logic
| Component28 | 99 | 5 | Data
| Component29 | 116 | 8 | Logic
| Component30 | 68 | 5 | Calculation
| Component31 | 52 | 4 | Data
| Component32 | 27 | 3 | Data
| Component33 | 106 | 6 | I/O
| Component34 | 76 | 6 | Logic
| Component35 | 39 | 3 | Calculation
| Component36 | 86 | 6 | I/O
| Component37 | 105 | 8 | I/O
| Component38 | 12 | 2 | Logic
| Component39 | 165 | 11 | Logic
| Component40 | 168 | 12 | Data
| Component41 | 57 | 4 | Logic
| Component42 | 80 | 6 | Calculation
| Component43 | 126 | 8 | Data
| Component44 | 185 | 13 | Data
| Component45 | 36 | 2 | Data
| Component46 | 72 | 5 | Logic
| Component47 | 30 | 1 | Data
| Component48 | 19 | 1 | Logic
| Component49 | 17 | 1 | I/O
| Component50 | 86 | 6 | Calculation
| Component51 | 42 | 4 | Calculation
| Component52 | 57 | 3 | Logic
| Component53 | 103 | 6 | I/O
| Component54 | 220 | 14 | Calculation
| Component55 | 70 | 5 | Logic
| Component56 | 63 | 4 | Data
| Component57 | 114 | 7 | Calculation
| Component58 | 149 | 10 | Data
| Component59 | 58 | 3 | Calculation
| Component60 | 36 | 2 | Logic
| Component61 | 114 | 7 | I/O
| Component62 | 139 | 9 | Calculation
| Component63 | 13 | 1 | Data
| Component64 | 10 | 1 | Calculation
| Component65 | 2 | 1 | Logic
| Component66 | 27 | 1 | Calculation
| Component67 | 16 | 1 | Logic
| Component68 | 21 | 1 | Logic
| Component69 | 136 | 8 | Calculation
| Component70 | 168 | 12 | Data
| Component71 | 218 | 14 | Logic
| Component72 | 112 | 7 | Logic
| Component73 | 92 | 6 | I/O
| Component74 | 47 | 4 | Calculation
| Component75 | 90 | 6 | Data
| Component76 | 103 | 7 | Logic
| Component77 | 153 | 11 | Calculation
| Component78 | 95 | 6 | I/O
| Component79 | 34 | 2 | Logic
| Component80 | 52 | 3 | Logic
| Component81 | 180 | 12 | I/O
| Component82 | 50 | 2 | Calculation
| Component83 | 109 | 8 | Calculation
| Component84 | 159 | 11 | Data
| Component85 | 37 | 1 | Data
| Component86 | 84 | 6 | Calculation
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea)
| Project1 | 691 | 669 | 712 | 2289 | 1384
| Project2 | 467 | 695 | 746 | 1267 | 1814
| Project3 | 472 | 529 | 481 | 1650 | 1290
| Project4 | 523 | 746 | 676 | 1418 | 1441
| Project5 | 256 | 277 | 232 | 534 | 483
| Project6 | 524 | 559 | 451 | 1174 | 962
| Project7 | 536 | 695 | 626 | 1345 | 1166
| Project8 | 352 | 348 | 389 | 796 | 2017
| Project9 | 429 | 472 | 415 | 1376 | 1184
| Project10 | 252 | 317 | 297 | 1224 | 907
| Project11 | 554 | 618 | 621 | 2257 | 1426
| Project12 | 508 | 449 | 474 | 2461 | 1478
| Project13 | 440 | 477 | 398 | 1086 | 970
| Project14 | 556 | 582 | 598 | 2148 | 1654
| Project15 | 403 | 430 | 357 | 1617 | 1049
| Project16 | 715 | 754 | 771 | 1630 | 2371
| Project17 | 362 | 393 | 410 | 916 | 1443
| Project18 | 600 | 631 | 567 | 1393 | 1726
| Project19 | 580 | 791 | 842 | 1298 | 2648
| Project20 | 443 | 593 | 583 | 2118 | 1618
Project History: The following describes the to-date percentages for development time and defects.
| Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
| Analysis | 11% | 5% | 0%
| Architecture | 8% | 9% | 0%
| Project planning | 1% | 0% | 0%
| Interation planning | 4% | 1% | 0%
| Construction | 48% | 78% | 29%
| Refactoring | 3% | 3% | 9%
| Review | 4% | 0% | 3%
| Integration test | 8% | 0% | 59%
| Repatterning | 2% | 0% | 0%
| Postmortem | 6% | 0% | 0%
| Sandbox | 5% | 5% | 0%
| Total | 100% | 100% | 100%
Architecture: The following CRC cards describe new development.
| Component Name | ForecastedComponent01
| Design Approach | OO
Superclass
| Component Type | I/O
| Collaborators | ForecastedComponent02, ForecastedComponent03
| Operations | 6 methods
| Notes | The functionality of this component is available by deleting 4 LOC from, modifying 3 LOC of, and adding 4 LOC to Component69.
| Component Name | ForecastedComponent02
| Design Approach | OO
| Superclass | ForecastedComponent06
| Component Type | I/O
| Collaborators | ForecastedComponent03, ForecastedComponent04
| Operations | 2 methods
| Notes | No base code approximates the functionality of this component. This component is most similar in complexity to Component82
| Component Name | ForecastedComponent03
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 5 methods
| Notes | No base code approximates the functionality of this component. This component is most similar in complexity to Component49
| Component Name | ForecastedComponent04
| Design Approach | OO
Superclass
| Component Type | Data
| Collaborators | ForecastedComponent05
| Operations | 8 methods
| Notes | No base code approximates the functionality of this component. This component is most similar in complexity to Component15
| Component Name | ForecastedComponent05
| Design Approach | OO
Superclass
| Component Type | Calculation
Collaborators
| Operations | 4 methods
| Notes | No base code approximates the functionality of this component. This component is most similar in complexity to Component24
| Component Name | ForecastedComponent06
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 2 methods
| Notes | No base code approximates the functionality of this component. This component is most similar in complexity to Component5

## Assignment
Process Information
Name: | Albert Wallace
Username: | aew0024
Assignment: | CA04
Instructor Assessment
Aspect | Possible Score | Score | Comment
Size matrix | 10
Component sizing | 15
Size and effort calculations | 20
Activity calculations | 5
Total | 50 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a value from a drop-down menu; do not indicate units (such as "min", "hr", "LOC", etc.) Please do not leave any boxes blank; I will assume that an empty box means you did not answer the question.
Parameters
normal
log-normal
not applicable
LOCE x Time
LOCA x Time
Productivity
NA - base component
VS
S
M
L
VL
not applicable
Calculation
Data
IO
Logic
not applicable
low
medium
high
Decision D
not applicable
Size matrix
| Low | Mid | High
VS | 2 | 8 | 10 | LOC/Method
S | 10 | 11 | 13 | LOC/Method
M | 13 | 15 | 18 | LOC/Method
L | 18 | 21 | 25 | LOC/Method
VL | 25 | 29 | big | LOC/Method
Component sizing
Component | Relative Size | Raw New LOC
ForecastedComponent01 | L | 7 | LOC
ForecastedComponent02 | VL | 58 | LOC
ForecastedComponent03 | M | 75 | LOC
ForecastedComponent04 | L | 168 | LOC
ForecastedComponent05 | M | 60 | LOC
ForecastedComponent06 | M | 30 | LOC
Size and effort calculations
Total raw size (LOCr) | 398 | LOC
Planned size (LOCp) | 439 | LOC
Confidence | medium
Productivity (Prod) | 23 | LOC/hr
Planned effort (Ep) | 1198 | Minutes
Lower prediction interval (LPI) | 817 | Minutes
Upper prediction interval (UPI) | 2277 | Minutes
Confidence | medium
Activity calculations
Analysis | 132 | Minutes
Architecture | 96 | Minutes
Project planning | 12 | Minutes
Interation Planning | 48
Construction | 575 | Minutes
Refactoring | 36 | Minutes
Review | 48 | Minutes
Integration Test | 96 | Minutes
Repatterning | 24 | Minutes
Postmortem | 72 | Minutes
Sandbox | 60 | Minutes
Total | 1199 | Minutes

## Calc-1
Supporting Calculations for
Size matrix
Identifier | LOC/method | ln(LOC/method)
Component1 | 16.7 | 2.8154
Component2 | 14.9231 | 2.7029
Component3 | 15.6667 | 2.7515 | Average of ln(LOC/method)
Component4 | 14.4444 | 2.6703 | 2.7051
Component5 | 13.5 | 2.6027
Component6 | 16.1667 | 2.783 | Stdev of ln(LOC/method
Component7 | 14 | 2.6391 | 0.3177
Component8 | 14.5 | 2.6741
Component9 | 14 | 2.6391
Component10 | 14.9091 | 2.702
Component11 | 15.4 | 2.7344 | VS- | VS | VS+
Component12 | 15.5 | 2.7408 | [2] | 8 | 10
Component13 | 15.6667 | 2.7515
Component14 | 11 | 2.3979 | _S- | _S | _S+
Component15 | 18 | 2.8904 | 10 | 11 | 13
Component16 | 12.8571 | 2.5539
Component17 | 19 | 2.9444 | _M- | _M | _M+
Component18 | 14.25 | 2.6568 | 13 | 15 | 18
Component19 | 15.7143 | 2.7546
Component20 | 19 | 2.9444 | _L- | _L | _L+
Component21 | 14.8571 | 2.6985 | 18 | 21 | 25
Component22 | 13.3 | 2.5878
Component23 | 14.4 | 2.6672 | VL- | VL | VL+
Component24 | 15.1538 | 2.7183 | 25 | 29 | [BIG]
Component25 | 13.0909 | 2.5719
Component26 | 14.9333 | 2.7036
Component27 | 19 | 2.9444
Component28 | 19.8 | 2.9857
Component29 | 14.5 | 2.6741
Component30 | 13.6 | 2.6101
Component31 | 13 | 2.5649
Component32 | 9 | 2.1972
Component33 | 17.6667 | 2.8717
Component34 | 12.6667 | 2.539
Component35 | 13 | 2.5649
Component36 | 14.3333 | 2.6626
Component37 | 13.125 | 2.5745
Component38 | 6 | 1.7918
Component39 | 15 | 2.7081
Component40 | 14 | 2.6391
Component41 | 14.25 | 2.6568
Component42 | 13.3333 | 2.5903
Component43 | 15.75 | 2.7568
Component44 | 14.2308 | 2.6554
Component45 | 18 | 2.8904
Component46 | 14.4 | 2.6672
Component47 | 30 | 3.4012
Component48 | 19 | 2.9444
Component49 | 17 | 2.8332
Component50 | 14.3333 | 2.6626
Component51 | 10.5 | 2.3514
Component52 | 19 | 2.9444
Component53 | 17.1667 | 2.843
Component54 | 15.7143 | 2.7546
Component55 | 14 | 2.6391
Component56 | 15.75 | 2.7568
Component57 | 16.2857 | 2.7903
Component58 | 14.9 | 2.7014
Component59 | 19.3333 | 2.9618
Component60 | 18 | 2.8904
Component61 | 16.2857 | 2.7903
Component62 | 15.4444 | 2.7372
Component63 | 13 | 2.5649
Component64 | 10 | 2.3026
Component65 | 2 | 0.69315
Component66 | 27 | 3.2958
Component67 | 16 | 2.7726
Component68 | 21 | 3.0445
Component69 | 17 | 2.8332
Component70 | 14 | 2.6391
Component71 | 15.5714 | 2.7454
Component72 | 16 | 2.7726
Component73 | 15.3333 | 2.73
Component74 | 11.75 | 2.4639
Component75 | 15 | 2.7081
Component76 | 14.7143 | 2.6888
Component77 | 13.9091 | 2.6325
Component78 | 15.8333 | 2.7621
Component79 | 17 | 2.8332
Component80 | 17.3333 | 2.8526
Component81 | 15 | 2.7081
Component82 | 25 | 3.2189
Component83 | 13.625 | 2.6119
Component84 | 14.4545 | 2.671
Component85 | 37 | 3.6109
Component86 | 14 | 2.6391

## Calc-2
Supporting Calculations for
Component sizing
Component | Method Count | Notes | Relative to | Attributes of Relative: | Resulting size bucket: | Expected LOC/M | Expected LOC total | Notes
ForecastC01 | 6 | LOC: D4, M3, A4 | Component 69 | LOC 136 (so FC01 = 139 LOC total) | L (not medium; based on known LOC change) | 21 | 126 | LOC really 139; count as 7 LOC to add/modify
ForecastC02 | 2 | - | Component 82 | LOC/M 25 | VL | 29 | 58 | -
ForecastC03 | 5 | - | Component 49 | LOC/M 17 | M | 15 | 75 | -
ForecastC04 | 8 | - | Component 15 | LOC/M 18 | L | 21 | 168 | -
ForecastC05 | 4 | - | Component 24 | LOC/M 15.15 | M | 15 | 60 | -
ForecastC06 | 2 | - | Component 5 | LOC/M 13.5 | M | 15 | 30 | -
|  |  | FC01 estimated lines/method | 139/6 or | Overall LOCraw
|  |  | = | 23.1667 | without FC01 | 391
|  |  | (This value was calculated to determine true size bucket) |  | with FC01 | 398

## Calc-3
Supporting Calculations for
Size and effort calculations
Given LOCraw =
398
Use past projects to estimate LOCplanned. Given this data…
Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) |  | Sum(LOCr) from past | Sum(LOCa) from past
Project1 | 691 | 669 | 712 |  | 9663 | 10646
Project2 | 467 | 695 | 746
Project3 | 472 | 529 | 481 |  | Sum(actual)/Sum(raw) from the past:
Project4 | 523 | 746 | 676 |  | 1.1017
Project5 | 256 | 277 | 232 |  | (So our calculationes resulted in us underestimating by about 10%)
Project6 | 524 | 559 | 451
Project7 | 536 | 695 | 626 |  | For THIS project, what should we plan to see?
Project8 | 352 | 348 | 389 |  | LOC(planned) =
Project9 | 429 | 472 | 415 |  | 439
Project10 | 252 | 317 | 297
Project11 | 554 | 618 | 621 |  | How about confidence for the size calculation? First confidence value:
Project12 | 508 | 449 | 474 |  | Confidence value = | square correl(LOCr, LOCa)
Project13 | 440 | 477 | 398 |  | 0.67497 | Giving us a medium confidence
Project14 | 556 | 582 | 598
Project15 | 403 | 430 | 357
Project16 | 715 | 754 | 771
Project17 | 362 | 393 | 410
Project18 | 600 | 631 | 567
Project19 | 580 | 791 | 842
Project20 | 443 | 593 | 583
And more, to calulate effort…
Identifier | Planned Effort (Ep) | Actual Effort (Ea) | Actual Effort, Hours | Actual LOC / Actual Hours Spent | Ea/LOCa |  | Effort Calculaton
Project1 | 2289 | 1384 | 23.0667 | 30.8671 | 1.9438 | Prod = | 23 | LOC/hr
Project2 | 1267 | 1814 | 30.2333 | 24.6748 | 2.4316 | sum(Ea)/sum(LOCa) = | 2.7269
Project3 | 1650 | 1290 | 21.5 | 22.3721 | 2.6819 | Ep = | 1197.1265
Project4 | 1418 | 1441 | 24.0167 | 28.1471 | 2.1317 | LPI = | 817
Project5 | 534 | 483 | 8.05 | 28.8199 | 2.0819 | UPI = | 2277
Project6 | 1174 | 962 | 16.0333 | 28.1289 | 2.133 | confidence = | 0.55663 | medium
Project7 | 1345 | 1166 | 19.4333 | 32.2127 | 1.8626
Project8 | 796 | 2017 | 33.6167 | 11.5716 | 5.1851
Project9 | 1376 | 1184 | 19.7333 | 21.0304 | 2.853
Project10 | 1224 | 907 | 15.1167 | 19.6472 | 3.0539
Project11 | 2257 | 1426 | 23.7667 | 26.129 | 2.2963
Project12 | 2461 | 1478 | 24.6333 | 19.2422 | 3.1181
Project13 | 1086 | 970 | 16.1667 | 24.6186 | 2.4372
Project14 | 2148 | 1654 | 27.5667 | 21.6929 | 2.7659
Project15 | 1617 | 1049 | 17.4833 | 20.4194 | 2.9384
Project16 | 1630 | 2371 | 39.5167 | 19.5108 | 3.0752
Project17 | 916 | 1443 | 24.05 | 17.0478 | 3.5195
Project18 | 1393 | 1726 | 28.7667 | 19.7103 | 3.0441
Project19 | 1298 | 2648 | 44.1333 | 19.0785 | 3.1449
Project20 | 2118 | 1618 | 26.9667 | 21.6193 | 2.7753
Average LOC/Hr, rounded
23

## Calc-4
Supporting Calculations for
Activity calculations
Given
(rel to 1198 min)
Phase | Time in Phase To Date % |  | Percentage as Decimal | Time spent, in minutes
Analysis | 11% | 11 | 0.11 | 132
Architecture | 8% | 8 | 0.08 | 96
Project planning | 1% | 1 | 0.01 | 12
Interation planning | 4% | 4 | 0.04 | 48
Construction | 48% | 48 | 0.48 | 575
Refactoring | 3% | 3 | 0.03 | 36
Review | 4% | 4 | 0.04 | 48
Integration test | 8% | 8 | 0.08 | 96
Repatterning | 2% | 2 | 0.02 | 24
Postmortem | 6% | 6 | 0.06 | 72
Sandbox | 5% | 5 | 0.05 | 60
Total | 100% |  |  | 1199 | (rounding issue left unresolved)